## Project3_GanttChart
Friday Lab Group Project 3 Gantt Chart
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Decide on a Project
| Come Up With an Idea (flappy bird KU prototype) | 2019-03-22 | 2019-03-29 | 6 | All | 100% | bar: WEEK 1 F to WEEK 2 F; WEEK 4 M to WEEK 4 T
| Decide on a Language (JS, HTML) | 2019-03-22 | 2019-03-29 | 6 | All | 100% | bar: WEEK 1 F to WEEK 2 F; WEEK 4 M to WEEK 4 T
| Assign Team Roles | 2019-03-22 | 2019-03-29 | 6 | All | 100% | bar: WEEK 1 F to WEEK 2 F; WEEK 4 M to WEEK 4 T
Build Source Code
| Create Index HTML Page | 2019-03-29 | 2019-04-02 | 3 | Jason | 100% | bar: WEEK 2 M to WEEK 3 T; WEEK 4 M to WEEK 4 T
| Create Bird.js | 2019-03-29 | 2019-04-02 | 3 | Hanwen | 100% | bar: WEEK 2 M to WEEK 3 T; WEEK 4 M to WEEK 4 T
| RunGame() Initialization | 2019-04-02 | 2019-04-05 | 4 | Saharsh | 100% | bar: WEEK 3 T to WEEK 4 T
| Create and Initialize Sounds | 2019-04-02 | 2019-04-05 | 4 | Saharsh | 100% | bar: WEEK 3 T to WEEK 4 T
| Bird Movement | 2019-04-02 | 2019-04-06 | 4 | All | 100% | bar: WEEK 3 T to WEEK 4 T
| Create Obstacles | 2019-04-02 | 2019-04-06 | 4 | All | 100% | bar: WEEK 3 T to WEEK 4 T
| Create Game Over Condition | 2019-04-03 | 2019-04-06 | 3 | Jason | 100% | bar: WEEK 3 T to WEEK 4 T
| Create and Implement Images | 2019-04-02 | 2019-04-09 | 6 | Aris | 100% | bar: WEEK 3 T to WEEK 4 T
Finalize Documentation
| Gantt Chart | 2019-03-22 | 2019-04-09 | 13 | Aris | 100% | bar: WEEK 1 F to WEEK 4 T
| Standard Documentation | 2019-04-07 | 2019-04-09 | 2 | Hanwen | 100% | bar: WEEK 4 M to WEEK 4 T
| Scrum Artifacts | 2019-04-07 | 2019-04-09 | 2 | Aris | 100% | bar: WEEK 4 M to WEEK 4 T
| UML (State, Use Case, Class) | 2019-04-07 | 2019-04-09 | 2 | Jason | 100% | bar: WEEK 4 M to WEEK 4 T
Project 4 Goals
| Restart Button | 2019-04-10 | 2019-04-15 | 4 | Aris | 0% | bar: WEEK 4 M to WEEK 5 M
| High Score Counter | 2019-04-12 | 2019-04-17 | 4 | Saharsh | 0% | bar: WEEK 4 M to WEEK 4 T; WEEK 4 F to WEEK 5 W
| Play Against Friends | 2019-04-17 | 2019-04-30 | 10 | Jason, Hanwen | 0% | bar: WEEK 4 M to WEEK 4 T; WEEK 5 Th to WEEK 7 T
| Random Powerups | 2019-04-17 | 2019-04-30 | 10 | Aris, Saharsh | 0% | bar: WEEK 4 M to WEEK 4 T; WEEK 5 Th to WEEK 7 T
| Continue Documentation | 2019-04-10 | 2019-04-30 | 15 | All | 0% | bar: WEEK 4 M to WEEK 7 T
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])