## Project3_GanttChart
Friday Lab Group Project 4 Gantt Chart
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Decide on a Project
| Come Up With an Idea (flappy bird KU prototype) | 2019-03-22 | 2019-03-29 | 6 | All | 100% | bar: WEEK 1 F to WEEK 2 F; WEEK 4 M to WEEK 4 T; WEEK 4 F
| Decide on a Language (JS, HTML) | 2019-03-22 | 2019-03-29 | 6 | All | 100% | bar: WEEK 1 F to WEEK 2 F; WEEK 4 M to WEEK 4 T; WEEK 4 F
| Assign Team Roles | 2019-03-22 | 2019-03-29 | 6 | All | 100% | bar: WEEK 1 F to WEEK 2 F; WEEK 4 M to WEEK 4 T; WEEK 4 F
Build Source Code
| Create Index HTML Page | 2019-03-29 | 2019-04-02 | 3 | Jason | 100% | bar: WEEK 2 M to WEEK 3 T; WEEK 4 M to WEEK 4 T; WEEK 4 F
| Create Bird.js | 2019-03-29 | 2019-04-02 | 3 | Hanwen | 100% | bar: WEEK 2 M to WEEK 3 T; WEEK 4 M to WEEK 4 T; WEEK 4 F
| RunGame() Initialization | 2019-04-02 | 2019-04-05 | 4 | Saharsh | 100% | bar: WEEK 3 T to WEEK 4 T; WEEK 4 F
| Create and Initialize Sounds | 2019-04-02 | 2019-04-05 | 4 | Saharsh | 100% | bar: WEEK 3 T to WEEK 4 T; WEEK 4 F
| Bird Movement | 2019-04-02 | 2019-04-06 | 4 | All | 100% | bar: WEEK 3 T to WEEK 4 T; WEEK 4 F
| Create Obstacles | 2019-04-02 | 2019-04-06 | 4 | All | 100% | bar: WEEK 3 T to WEEK 4 T; WEEK 4 F
| Create Game Over Condition | 2019-04-03 | 2019-04-06 | 3 | Jason | 100% | bar: WEEK 3 T to WEEK 4 T; WEEK 4 F
| Create and Implement Images | 2019-04-02 | 2019-04-09 | 6 | Aris | 100% | bar: WEEK 3 T to WEEK 4 T; WEEK 4 F
Finalize Documentation
| Gantt Chart | 2019-03-22 | 2019-04-09 | 13 | Aris | 100% | bar: WEEK 1 F to WEEK 4 T; WEEK 4 F
| Standard Documentation | 2019-04-07 | 2019-04-09 | 2 | Hanwen | 100% | bar: WEEK 4 M to WEEK 4 T; WEEK 4 F
| Scrum Artifacts | 2019-04-07 | 2019-04-09 | 2 | Aris | 100% | bar: WEEK 4 M to WEEK 4 T; WEEK 4 F
| UML (State, Use Case, Class) | 2019-04-07 | 2019-04-09 | 2 | Jason | 100% | bar: WEEK 4 M to WEEK 4 T; WEEK 4 F
Project 4 Sprint
| Restart Button | 2019-04-10 | 2019-04-15 | 4 | Aris | 100% | bar: WEEK 4 M to WEEK 5 M
| Improved Timer | 2019-04-12 | 2019-04-17 | 4 | Saharsh | 100% | bar: WEEK 4 M to WEEK 4 T; WEEK 4 F to WEEK 5 W
| Extra Lives | 2019-04-12 | 2019-04-17 | 4 | Hanwen | 100% | bar: WEEK 4 M to WEEK 4 T; WEEK 4 F to WEEK 5 W
| 2 Player Mode | 2019-04-17 | 2019-04-30 | 10 | Jason, Hanwen | 100% | bar: WEEK 4 M to WEEK 4 T; WEEK 4 F; WEEK 5 Th to WEEK 7 T
| Mushroom Mode | 2019-04-17 | 2019-04-30 | 10 | Aris, Saharsh | 100% | bar: WEEK 4 M to WEEK 4 T; WEEK 4 F; WEEK 5 Th to WEEK 7 T
| Project 4 Presentation | 2019-05-03 | 2019-05-03 | 1 | All | 100% | bar: WEEK 4 M to WEEK 4 T; WEEK 4 F; WEEK 7 F
| Project 4 Documentation | 2019-04-10 | 2019-05-08 | 21 | All | 100% | bar: WEEK 4 M to WEEK 8 W
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])