## Sheet1
Agile Product Backlog
Friday Lab Group Project 4
Task Name | Description | Time Estimate | Status
Sprint 1-Project 3 | - | Hours | Complete
Decide Project | Decide on an Idea for Project 3 | 1 | Complete
Decide Language | Decide Best Languages to Accomplish Project 3 | 0.5 | Complete
Assign Team Roles | Assign a job to each team member for completion | 0.5 | Complete
Images | Create Images for Bird, Pipes, Background | 1 | Complete
Sounds | Create Background Sounds and Effects | 1 | Complete
HTML Page | Create HTML Index to display images | 2 | Complete
Bird.js | Specific Functions Below | {12} | Complete
Constructor | Draws Bird Object and Determines Position | 2 | Complete
CreateMap | Creates Map on Background | 1 | Complete
Move Functionality | Moves the bird forward on time and up when clicked | 3 | Complete
RunGame | Plays sound, calls timer and constructor | 2 | Complete
Obstacle | Creates the Pipes to Be Avoided | 2 | Complete
Game Over | Lose Condition called if pipe or border hit | 2 | Complete
Documentation | All Documentation for Project | {5} | Complete
Std. Documentation | Standard Documentation | 1 | Complete
UML | State Diagram, Case Diagram, Class Diagram | 2 | Complete
Gantt Chart | Agile Gantt Chart to keep track of progress | 1 | Complete
Scrum Artifacts | Sprint Backlog and Product Backlog | 1 | Complete
Sprint 2-Project 4 | - | - | Complete
Extra Lives | Add multiple lives for each bird | 4 | Complete
Play Against Friends | Allows User to Play with a Friend | 3 | Complete
Mushroom Powerup | Adds Extra life, turns into Jayhawk | 3 | Complete
Timer | Creates a nice looking timer to keep score | 2 | Complete
Test Suite | Tests Several Game Functionalities | 3 | Complete
Restart Button | Allows User to restart without refreshing | 1 | Complete

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started